## RCS GanttChart
RCS Gantt Chart
zoneyung
| Project Start Date | 2025-11-08 |  |  |  | Display Week | 7 |  | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
| Project Lead | [7 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02
 | time axis 2025-12-15 to 2026-02-08
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-12-15 to 2026-02-08
1 | 前期优化 |  |  |  | - |  |  | -
1.1 | 系统总体改版规划与架构重组 | 陆晓涛 |  | 2025-11-08 | 2025-11-18 | 11 | 100% | 7
1.2 | 堆垛车设备模型扩展与注册机制 | 陆晓涛 |  | 2025-11-08 | 2025-11-12 | 5 | 100% | 3
1.3 | 三维路径模型与节点定义 | 陆晓涛 |  | 2025-11-13 | 2025-11-14 | 2 | 100% | 2
1.4 | 升降与叉取动作执行模块 | 陆晓涛 |  | 2025-11-15 | 2025-11-18 | 4 | 100% | 2
1.5 | 任务调度与分配逻辑改造 | 陆晓涛 |  | 2025-11-19 | 2025-11-20 | 2 | 100% | 2
1.6 | 与信捷沟通确认协议 | 陆晓涛 |  | 2025-11-10 | 2025-11-20 | 11 | 100% | 9
1.7 | 通信协议扩展与适配 | 陆晓涛 |  | 2025-11-21 | 2025-11-23 | 3 | 100% | 1
2 | 与设备联调 |  |  |  | - |  |  | -
2.1 | TCP/IP协议对接 | 陆晓涛 |  | 2025-11-24 | 2025-11-26 | 3 | 100% | 3
2.2 | 指令下发测试 | 陆晓涛 |  | 2025-11-27 | 2025-11-28 | 2 | 100% | 2
2.3 | 行走/转弯运行 | 陆晓涛 |  | 2025-11-29 | 2025-11-30 | 2 | 100% | 0
2.4 | 取放货动作 | 陆晓涛 |  | 2025-12-01 | 2025-12-03 | 3 | 100% | 3
2.5 | 充电/待机功能测试 | 陆晓涛 |  | 2025-12-04 | 2025-12-05 | 2 | 100% | 2
2.6 | 多车运行算法测试 | 陆晓涛 |  | 2025-12-06 | 2025-12-08 | 3 | 0% | 1
3 | 系统完整性开发 |  |  |  | - |  |  | -
3.1 | *区域划分功能 | 陆晓涛 |  | 2025-12-10 | 2025-12-25 | 16 | 100% | 12
3.1.1 | 增加区域管理模式 |  |  | 2025-12-10 | 2025-12-10 | 1 | 100%
3.1.2 | 添加区域功能（起点、终点、区域名 |  |  | 2025-12-11 | 2025-12-11 | 1 | 100%
3.1.3 | 页面加载渲染显示区域画面 |  |  | 2025-12-12 | 2025-12-12 | 1 | 100%
3.1.4 | 区域删除功能 |  |  | 2025-12-13 | 2025-12-13 | 1 | 100%
3.1.5 | 后端数据库模型和接口开发 |  |  | 2025-12-14 | 2025-12-15 | 2 | 100%
3.1.6 | 区域绑定AGV（一对多） |  |  | 2025-12-16 | 2025-12-17 | 2 | 100%
3.1.7 | 多个区域可绑定同一个区域ID |  |  | 2025-12-18 | 2025-12-18 | 1 | 100%
3.1.8 | 区域控制任务分配管控 |  |  | 2025-12-19 | 2025-12-21 | 3 | 100%
3.1.9 | 区域控制路径与交管算法控制 |  |  | 2025-12-22 | 2025-12-24 | 3 | 100%
3.1.10 | 功能测试，code review |  |  | 2025-12-25 | 2025-12-25 | 1 | 100%
3.2 | 配合汇川调试堆垛车 | 张超 |  | 2025-12-15 | 2025-12-25 | 11 | 0%
3.3 | *滚筒输送线对接整改 | 陆晓涛 |  | 2025-12-22 | 2025-12-31 | 10 | 0% | 8
3.4 | *多作业方向区域控制 | 陆晓涛 |  | 2026-01-03 | 2026-01-16 | 14 | 0% | 10
3.5 | 登录页面优化 | 陆晓涛 |  | 2026-01-17 | 2026-01-22 | 6 | 0% | 4
3.6 | 监控板日志输出组件 | 陆晓涛 |  | 2026-01-23 | 2026-01-30 | 8 | 0% | 6
4 | 功能升级 |  |  |  | - |  |  | -
4.1 | 导入导出由csv改为xlsx | 陆晓涛 |  | 2026-01-31 | 2026-02-05 | 6 | 0% | 4
4.2 | 充电策略动态配置 | 陆晓涛 |  | 2026-02-06 | 2026-02-14 | 9 | 0% | 6
4.3 | 交管防撞细化到车身角度 | 陆晓涛 |  | 2026-02-24 | 2026-03-10 | 15 | 0% | 11
4.4 | RCS开放平台 | 张超 |  | 2025-12-26 | 2026-01-12 | 18 | 0% | 12
4.5 | 多种车型兼容 | 陆晓涛 |  | 2026-03-11 | 2026-03-18 | 8 | 0% | 6
4.6 | 页面优化（dashboard为主） | 陆晓涛 |  | 2026-03-19 | 2026-03-31 | 13 | 0% | 9
4.7 | 解析CAD初始化地图 | 张超 |  | 2026-01-13 | 2026-01-26 | 14 | 0% | 10
4.8 | 二进制报文存储方案 | 张超 |  | 2026-01-27 | 2026-02-05 | 10 | 0%
4.9 | 数据中心（监控面板+信息采集） | 张超 |  | 2026-02-06 | 2026-02-28 | 23 | 0%
4.10 | 地图监控3D化（数字孪生） |  |  | 2026-04-01 | 2026-04-20 | 20 | 0%
4.11 | 网关前端可视化 |  |  | 2026-04-01 | 2026-04-15 | 15 | 0%
4.12 | 系统部署工具 | 张超 |  | 2026-03-01 | 2026-03-10 | 10 | 0%
4.13 | 地图绘制增强 |  |  | 2026-04-01 | 2026-04-15 | 15 | 0%
4.14 | 移动端APP（检测与控制） | 张超 |  | 2026-03-10 | 2026-03-31 | 22 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.